## ??
?? | ??
??? | 2026-06-13
??? | C:/smartreturn-pro
??? | smartreturn-pro
?? ?? | AGENTS.md, smartreturn-pro-workflow.md, smartreturn-pro-menu-and-screen-map.md, smartreturn-pro-mvp-scope.md
?? ?? ? | 50
??? ?? | ???/??/API/???/closeout ?? ?? ??? ??? ?? ??
?? ?? | ?? MVP, ????, import, ??/??, ?? ??? ?? ? ??. ??/??/OMS/??/Local Agent? ?? ?? ??.

## ??? ??
??? | ??? | ?? ?? | ??? | ?? ?? | ?? ?? | ??? | ?? ?? | ??? ???? | ????
???? | ?? ???? | ????? | ?? ??? | /dashboard | ?? ?? | 45% | DashboardPage ?? ??, ?? ??? ??? | ?? KPI API? ?? ?? ???? ??? | P1
???? | ?? ?? | ????? | ?? ???, ??? | /dashboard | ?? ?? | 35% | ???? ? ?? ?? ?? ?? | ??? ?? ?? ??? ?? ? ?? ?? | P1
???? | ??? ?? | ??? ??? | ?? ??? | /master/clients | ?? ?? | 75% | ??/??/????/????/??????? ??? API ?? | ?? CRUD ?? ??, ?? ???? ?? ?? | P0
???? | ?? ?? | ??? ??? | ?? ???, ??? ??? | /master/products | ?? ?? | 70% | ??/??? API? ?? ?? ?? | ?? ?? ??/?? UX ??, ??/??? ?? | P0
???? | ?? ?? | ??? ??? | ?? ??? | ??? ?? ?? | ?? ?? | 60% | ?? API? ???-?? ?? ?? ?? | ?? ?? ??, ??/? ?? | P0
???? | ???? ?? | ??? ??? | ?? ??? | /master/common-codes | ?? ?? | 75% | ???? ??/?? CRUD API? ?? ?? | ??/?? ?? ?? ?? | P0
???? | ???/?? ?? | ??? ??? | ?? ??? | ??? | ?? | 25% | ???/?? seed/???? ?? API? ??? ?? ??? disabled | ??? ??, role ??, ???? ??? ?? ?? | P0
?? | ???? ?? | ???/??? | ?? ??? | /returns/intake | ?? ?? | 80% | ?? ?? ??/?/??/???? API? ?? ?? | ??? ?? ???, ?? ?? ??, ?? ?? UX ?? | P0
?? | ???/?? | ??? ??? | ?? ??? | /returns/unit-assignment | ?? ? | 70% | client_unit ?? ??? API ?? ?? | ?? ??? ?? ??? ???? ?? | P0
?? | ???? ?? | ??? ??? | ??? | /returns/processing | ?? ?? | 78% | ??/?? row/??/?? API? ?? ??. ?? ??? ??? | ?? ?? Local Agent ??, ?? Object Storage ?? | P0
?? | ?? ?? | ??/??? | ?? ??? | /returns/closing | ?? ?? | 75% | ?? ?? ??/?? ? ?? ??? ?? ?? ?? | ??? ?? ???, ?? ??/?? ?? | P0
?? | ?? ?? | ??? ??? | ?? ???, ??? | /returns/external-outbound | ?? ? | 70% | ???? ??/?? API? ?? ?? | ?? batch ??/???/?? ?? | P0
?? | ???? ?? | ??? ??? | ?? ??? | /returns/external-outbound/batches | ?? ? | 68% | ???? batch ??/?? API? ?? ?? | batch ?? ?? ??? ?? ?? | P1
?? | ???? | ??? ??? | ?? ??? | /returns/hold | ?? ? | 70% | ?? ??/????/??? API? ?? ?? | ??? ?? ?? ??, SLA/?? | P1
?? | ???? | ??? ??? | ?? ??? | /returns/disposal | ?? ? | 68% | ?? ??/?? API? ?? ?? | ?? ?? ??, ??/?? ?? | P1
?? | ?? ???? | ??? ??? | ?? ???, ??? ??? | /returns/history | ?? ? | 72% | ?? ?? API? ??/?? ?? ?? ?? | ?? ????, ?? ???/??/??/?? ?? | P1
?? | ???? ?? | ???/??? | ?? ??? | ??? | ?? ?? | 10% | ?? ??? ??, ?? import ?? ??? ?? | inbound import_type, ???, API ?? | P2
?? | ???? ?? | ??? ??? | ??? | ??? | ?? ?? | 5% | ?? SmartScanPanel ??? ?? | ?? scan_events? ???? ? ?? ?? ?? | P2
?? | ???? | ??/??? | ?? ??? | ??? | ?? ?? | 5% | ?? ??? ?? ??? ?? | ?? ?? API?? inventory_events ?? | P2
?? | ?? ???? | ??? ??? | ?? ???, ??? ??? | ??? | ?? ?? | 5% | ?? ??? ?? | ?? ??/scan ?? ?? ?? ?? | P2
?? | ???? ?? | ???/??? | ?? ??? | ??? | ?? ?? | 10% | ?? import ?? ??? ?? | outbound import? OMS ???? ?? | P2
?? | ???? ?? | ??? ??? | ??? | ??? | ?? ?? | 5% | ?? ?? ???? ??? ?? | ?? ?? ??, ??/?? ?? ?? | P2
?? | ???? | ??/??? | ?? ??? | ??? | ?? ?? | 5% | inventory_events ?? ?? ?? | ????/???? idempotency ?? | P2
?? | ?? ???? | ??? ??? | ?? ???, ??? ??? | ??? | ?? ?? | 5% | ?? ??? ?? | ?? ??/scan ?? ?? ?? ?? | P2
OMS | ???? ?? | ???/??? | ?? ???, ??? ??? | ??? | ?? ?? | 10% | ?? ERD/?? ??? ?? | ?? import_type, ?? ??, ?? ?? ?? ?? | P3
OMS | ?? ?? | ??? ??? | ?? ???, ??? ??? | ??? | ?? ?? | 5% | ?? ??? ?? | ??/???? API? ?? ?? | P3
OMS | ???? ?? | ??/??? | ?? ??? | ??? | ?? ?? | 5% | ?? ??? ?? | ?? ???? ?? ? ?? wave ?? | P3
OMS | ?? ???? | ??? ??? | ?? ???, ??? ??? | ??? | ?? ?? | 5% | ?? ??? ?? | ?? raw ???/?? ?? ?? ?? | P3
?? | ???? | ??? ??? | ?? ???, ??? ??? | /inventory/current | ?? ? | 65% | current_inventory ?? API? ?? ?? | ?? ??/??/?? ?? ??? | P1
?? | ???? | ??? ??? | ?? ??? | /inventory/events | ?? ? | 65% | inventory_events ?? API? ?? ?? | ??/?? ??? ??, source? ???? ?? | P1
?? | ???? | ??/??? | ?? ??? | ??? | ?? ?? | 15% | inventory_events ??? ?? | ??/??/?? ?? ???? API? ?? | P2
?? | ???? | ??? ??? | ?? ???, ??? | ??? | ?? | 10% | ?? ?? ???? ??? ?? | ?? ??, ?? ??, ?? ? ?? ??? ?? | P2
?? | ??/?? ?? | ??? ??? | ?? ??? | ??? | ?? ?? | 5% | ??? MVP ?? ?? | ?? ??? ?? ???/?? ?? ?? | P3
?? | ?? ?? | ??/??? | ?? ??? | ??? | ?? ?? | 5% | ?? ?? ???/?? ??? ?? | ??/??/?? ??? ?? ?? ?? ?? | P3
?? | ?? ?? | ??? ??? | ?? ??? | ??? | ?? ?? | 5% | ?? ??? ?? | ?? ??? ?? ??? ?? ?? | P3
?? | ?? ?? | ??/??? | ?? ??? | ??? | ?? ?? | 5% | ?? ??? ?? | ?? ??/??/??? ?? ?? | P3
?? | ????? | ??? ??? | ?? ???, ??? ??? | ??? | ?? ?? | 5% | ?? ??? ?? | PDF/?? ??, ?? ?? ?? | P3
??/?? | ??? ?? | ??? ??? | ?? ??? | ?? ?? | ?? ?? | 45% | ?? ??/??? dry-run ?? ?? | ??? API ??/??? ??/???? ?? ?? | P2
??/?? | ERP ?? | ??? ??? | ?? ??? | ??? | ?? ?? | 5% | MVP ?? ?? | outbox/??/??? ?? ?? | P4
??/?? | ???? ?? | ??? ??? | ?? ??? | ??? | ?? ?? | 10% | ???? ? ?? ?? ?? ?? ??? | ?? ?? ??? ??, ????? ?? | P3
??/?? | ?? ?? ?? | ??? ??? | ?? ??? | /channels/accounts | ?? ? | 65% | channels API, raw_events, return_candidates, product_mappings ?? | ?? provider connector, ?? ??, ?? ???? | P1
??/?? | Local Agent ?? | ??? ??? | ?? ??? | ??? | ?? ?? | 5% | local_agent placeholder ?? ?? ?? | ?? ??/??? ??/?? health API ?? | P2
??/?? | ??? ?? | ??? ??? | ?? ??? | ?? ?? | ?? ?? | 10% | ??/??? ?? ?? ?? | feature gate, plan limit, ?? ?? API ?? | P2
??? ?? | ?? ???? | ????? | ??? ??? | /portal/dashboard | ?? ?? | 40% | ?? ????/???? ??, ?? ?? ??? | ???? KPI API, ??/??, ? ?? ?? | P2
??? ?? | ?? ?? | ??? ??? | ??? ??? | ??? | ?? ?? | 5% | ?? ?? ??? | ?? MVP ?? read-only ?? | P3
??? ?? | ?? ?? | ??? ??? | ??? ??? | ??? | ?? ?? | 10% | inventory API? ??? ?? ??? ??? | client scope read-only ?? ?? ?? | P2
??? ?? | ?? ?? | ??? ??? | ??? ??? | /portal/returns | ?? ?? | 60% | ?? ?? ???? ?? ?? | ??? ??/?? ??, ?? ???? | P2
??? ?? | ?? ?? | ??? ??? | ??? ??? | ??? | ?? ?? | 5% | ?? MVP ?? ?? | ?????/?? ?? read-only ?? | P3
??? ?? | ?? ??? | ???/??? | ??? ??? | /portal/returns/intake | ?? ?? | 60% | ?? ?? ?? ??? ?? ?? | ??/?? ?? ??? ??, ??? ?? ??? | P2
???/?? | ??/??? | ??? ??? | ?? ??? | /settings/plans | ?? ?? | 45% | ??? ?? ?? ?? ?? | backend feature gate/??/plan_limits API ?? | P2

## ?? ?? ??
?? | ??/?? | ?? ?? | ??? | ?? ?? | ?? ????
??/?? | ??? ? auth context | ?? | 85% | ???, context, route guard, ?? ?? ?? disabled ?? | ??? ??/?? ??/???? ??
??/?? | ???? ?? ?? ?? | ?? | 80% | must_change_password ??? API ?? | ??? ??? ?? ??
?? UI | SmartPage/Toolbar/DataSection/Modal/ScanPanel | ?? ? | 70% | ?? ???? ?? ?? | ??? ?? Select/Modal? ?? lookup?? ??
?? Grid | SmartDataGrid wrapper | ?? ? | 65% | wrapper? toolbar/export helper ?? | ?? ??, ??/???, ?? export ?? ??
Import | import job ??/????/??/??/??/?? | ?? ?? | 80% | API/??/??? ?? ?? | ???? ??, ?? ?? ?? ??
???? | ???/??/????/??? API | ?? ?? | 80% | CRUD/enable/disable API? ??? ?? | ?? ?? ??, route ?? ??
?? | ?? ?? ??/?/??/???? | ?? ?? | 80% | batch/rows/validate/prepare ?? ?? | ?? ??/?? ??? ??
?? | ???? ??/?? row/?? | ?? ?? | 78% | manual row, judgement, attachment API ?? | Object Storage, ?? ??, ?? ??
?? | ???/???? | ?? ? | 75% | ?? ?? ? inventory_events/current_inventory ?? | ?? ??/??, ??? ?? ???
?? | ?? ??/????/raw event/return candidate | ?? ? | 65% | dry-run/mock event? ?? ?? API ?? | ?? provider, scheduler, ??? ?? ??
?? | ???/?? ??? ?? | ?? ? | 65% | ?? API? ?? ?? | ??/??/???? ??? ??
?? | ?? ?? ????/?? ??/?? ?? | ?? ?? | 55% | client area route? ?? ?? ?? ?? | ??/??/?? ?? ??
??/??/OMS | ???/?? ?? | ?? | 5% | ?? ??? ??? ?? | ?? MVP ? ?? import/scan/inventory ?? ???
?? | ???/?? | ?? | 5% | ???? ??? | ??/?? -> ?? -> ?? -> ?? ??? ??
Local Agent | ??/???/?? ?? | ?? | 5% | placeholder ?? ?? | ?? health, print job queue, ?? ??? ??

## ?? ???
?? | ?? | ?? ?? | ?? ?? | ????
0??: ?? ?? | ??/??/?? ??? | ? ??? ???? ??, ??, ?? ??? ?? ?? | ? ??? ???/??/?? ??? ?? ?? | ??
1??: P0 ??? | ?? MVP ??? ?? | ???? ??, ????, ???, ????, ????, import ?? ?? | ?? ???? ???? ??? ???? ?? | ??
2??: ?? UX/?? ?? | ?? UI? scope ??? | SmartLookupModal/CommonCodeSelect, ???/?? ??, ?? ?? ??, ???? ?? | ??? ?? Select/??? ?? ?? | ??
3??: ??/?? ?? | ??? ??? ?? ?? ?? | ?? return_candidates -> return_expected ??, ?? ?? ??/?? ??? | ??? ??? ?? ???? ????? ?? | ??
4??: ?? ?? ?? | ??/??/?? ?? | ????, ????, inventory_events ??/?? ?? | ??? ?? ?? ?? ?? ??? ???? ?? | ??
5??: ??/?? MVP | WMS ?? ?? | ????/????/????, ????/????/???? | ???? ??? import/scan/closing ?? ??? | ??
6??: OMS/?? | ?? SaaS ?? ? | ????, ????, ???? ??, ??/??, ?? ??/??/?? | ??? ???? ??/??/?? ?? ?? | ??
7??: Local Agent/AI | ?? ???? ?? ?? | ?? ??, ??? ??, AI ?? ???, ?? ?? ?? | AI? ??? ?? ?? ??? ???? ?? | ??

## ?? ??
?? | ?? ??/?? | ?? ??
???? ?? | AGENTS.md | agency_id/client_id/client_unit_id/warehouse_id ?? SaaS, ?? ?? ??
?? ???? | docs/skills/smartreturn-pro-workflow.md | ?? ? remote/branch/status/AGENTS ??, ?? ?? ?? ??
?? | docs/skills/git-security-check.md | secret/env/config/logs/dist/build/cache/zip/exe ?? ??
?? ?? ?? | docs/business/smartreturn-pro-menu-and-screen-map.md | ????/????/??/??/??/OMS/??/??/??/?? ?? ?? ??
MVP ?? | docs/business/smartreturn-pro-mvp-scope.md | 1? MVP? ????, ??, import job, ?? ???, ?? ?? ??
?? ??? | frontend/src/routes/router.tsx | ?? ??? ??/?? route ??
?? ?? | frontend/src/layouts/MainLayout.tsx | ?? ?? ??? disabled ??? ?? ??
Backend API | backend/app/main.py, backend/app/routers/*.py | auth/password/master/channels/imports/returns/inventory router ?? ??